## Defect Tracker
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2026-02-05 | IVR prefix text displayed before responses in UI | Sprint 1 | Frontend Developer | UI Defect | Updated show() function to remove 'IVR:' prefix from screen display | 2025-02-06 | Closed | Resolved by cleaning display text
2 | 2026-02-10 | Invalid keypad digit not clearly handled in menu navigation | Sprint 1 | Backend Developer | Logic Defect | Added invalid option prompt in middleware process_menu() | 2026-02-12 | Closed | User now prompted with correct menu
3 | 2026-02-15 | Session error when Stop Call button pressed then keypad used | Sprint 2 | Backend Developer | Functional Defect | Added session validation before processing menu input | 2026-02-18 | Closed | Handled invalid session correctly
4 | 2026-02-20 | Speech recognition delay when microphone starts | Sprint 2 | Frontend Developer | Performance Defect | Optimized SpeechRecognition initialization logic | 2026-02-22 | Closed | Voice response improved
5 | 2026-02-24 | Unknown conversational text not properly handled | Sprint 2 | AI Developer | AI Logic Defect | Added fallback response in detect_intent() for unknown phrases | 2026-02-26 | Closed | System now asks user to repeat request
6 | 2026-03-05 | Analytics logs not recorded for first call event | Sprint 3 | Backend Developer | Backend Defect | Added logging inside start_call API endpoint | 2026-03-08 | Closed | Analytics endpoint now shows full call logs
7 | 2026-03-10 | Patient ID not processed correctly in mixed input | Sprint 4 | Backend Developer | Integration Defect | Synced conversation state with menu state (conv_state + current_menu) | 2026-03-10 | Closed | Patient ID now works in voice + keypad flow
8 | 2026-03-12 | Duplicate voice input displayed in UI | Sprint 4 | Frontend Developer | UI Defect | Fixed duplicate rendering in speech input handler | 2026-03-12 | Closed | Voice input shown only once
9 | 2026-03-18 | Deployment failure due to incorrect start command | Sprint 4 | Backend Developer | Deployment Defect | Updated start command to uvicorn main:app --host 0.0.0.0 --port $PORT | 2026-03-14 | Closed | Application deployed successfully
10 | 2026-03-20 | API URL mismatch between frontend and deployed backend | Sprint 4 | Frontend Developer | Integration Defect | Updated frontend API base URL to deployed endpoint | 2026-03-18 | Closed | Frontend successfully connected to live backend
11 | 2026-03-22 | Final system validation issues in report navigation | Sprint 4 | QA Engineer | Functional Defect | Fixed report menu navigation and return flow | 2026-03-20 | Closed | End-to-end IVR flow validated successfully