## Export Summary
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Product Backlog | Table 1 | Product Backlog
Sprint Backlog | Table 1 | Sprint Backlog
Stand up Meeting | Table 1 | Stand up Meeting
Retrospection | Table 1 | Retrospection

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | Web IVR interface for hospital services | Must Have | Frontend setup | Frontend Developer | Completed
Sprint 1 | Sprint 1 | US002 | Appointment booking via IVR | Must Have | Menu config | Backend Developer | Completed
Sprint 2 | Sprint 2 | US003 | Lab report status via IVR | Must Have | Lab module | Backend Developer | Completed
Sprint 2 | Sprint 2 | US004 | Billing enquiry via IVR | Should Have | Billing module | Backend Developer | Completed
Sprint 3 | Sprint 3 | US005 | Voice interaction using speech recognition | Must Have | AI module | AI Developer | Completed
Sprint 3 | Sprint 3 | US006 | Analytics for IVR usage | Could Have | Call logs | Backend Developer | Completed
Sprint 4 | Sprint 4 | US007 | Perform system testing (unit + integration testing) | Must Have | All modules | QA Engineer | Completed
Sprint 4 | Sprint 4 | US008 | Fix bugs and optimize IVR performance | Must Have | Testing results | Full Team | Completed
Sprint 4 | Sprint 4 | US009 | Deploy IVR system to cloud platform (Render) | Must Have | Backend + Frontend | Backend Developer | Completed
Sprint 4 | Sprint 4 | US010 | Validate deployed system and ensure end-to-end functionality | Must Have | Deployment | QA Engineer | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Complete Date | Task Owner | Activity | Status | Orginal Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
41
US001 | T1 | Design IVR frontend UI | 2026-02-01 | 2026-02-03 | Frontend Developer | UI Development | Done | 6 | bar: Day 1 to Day 2
US002 | T2 | Develop FastAPI IVR backend | 2026-02-04 | 2026-02-06 | Backend Developer | Backend API | Done | 8 | bar: Day 3 to Day 5
US003 | T3 | Lab report API | 2026-02-07 | 2026-02-09 | Backend Developer | API Logic | Done | 6 | bar: Day 4 to Day 5
US004 | T4 | Billing enquiry logic | 2026-02-10 | 2026-02-11 | Backend Developer | Billing Module | Done | 5 | bar: Day 6
US005 | T5 | Speech recognition integration | 2026-02-12 | 2026-02-15 | AI Developer | AI Integration | Done | 10 | bar: Day 6 to Day 9
US006 | T6 | Analytics endpoint | 2026-02-16 | 2026-02-18 | Backend Developer | Analytics | Done | 6 | bar: Day 8 to Day 11
US007 | T7 | Unit testing (API + modules) | 2026-02-20 | 2026-02-22 | QA Engineer | Testing | Done | 5 | bar: Day 11 to Day 12
US008 | T8 | Integration testing (IVR flow) | 2026-02-23 | 2026-02-25 | QA & Developer Team | System Testing | Done | 6 | bar: Day 12 to Day 13
US009 | T9 | Bug fixing & optimization | 2026-02-26 | 29-02-2026 | Full Team | Debugging | Done | 5 | bar: Day 13 to Day 14
US010 | T10 | Deployment on Render | 2026-03-03 | 2026-03-05 | Backend Developer | Deployment | Done | 5 | bar: Day 14
US011 | T11 | Final testing & validation | 2026-03-06 | 2026-03-10 | QA Engineer | Validation | Done | 4 | bar: Day 14

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Frontend API connection issue | Fixed API endpoint URL
Sprint 2 | Day 3 | Menu navigation bug | Debugged middleware
Sprint 2 | Day 4 | Speech recognition not detecting voice | Adjusted speech API config
Sprint 3 | Day 2 | Analytics logs missing | Added logging in backend
Sprint 4 | Day 2 | Patient ID not working with voice + keypad | Synchronized conversation and menu states
Sprint 4 | Day 3 | Duplicate voice input display | Fixed frontend duplication in speech handling
Sprint 4 | Day 4 | Deployment issues | Corrected start command and environment configuration

## Retrospection
SI | Sprint # | Sprint start date | Sprint end date | Team members | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 2026-02-01 | 2026-02-05 | Frontend & Backend | Define IVR requirements | Rushing UI | Team collaboration | Documented IVR features
2 | Sprint 2 | 2026-02-06 | 2026-02-10 | Backend Team | Write modular APIs | Hardcoding | Config-based menus | Refactored menu logic
3 | Sprint 3 | 2026-02-11 | 2026-02-15 | AI Developer | Improve voice AI | Ignoring edge cases | Test voice inputs | Added fallback intent
4 | sprint 4 | 2026-02-20 | 2026-03-05 | QA & Full Team | Perform testing & deploy application | Skipping test cases | Bug tracking | Fixed issues and deployed on Render